## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-1 | Introduction about Project, System Setup & Text handling | MUST HAVE | NA | Sree | 3- Completed
S1 | S1 | US-2 | introduction about project, system setup, multiprocessing , data base creation | SHOULD HAVE | NA | Sree | 2- In Progress
S2 | S2 | US-3 | Actual Implementation with chosing Proper Text Domain and etc | MUST HAVE | NA | Sree | 3- Completed
S2 | S2 | US-3 | Dynamic Chunking, Parallel Processing | MUST HAVE | NA | Sree | 3- Completed
S2 | S2 | US-3 | Connecting results to Database | MUST HAVE | NA | Sree | 3- Completed
S3 | S3 | US-4 | User interface Building | MUST HAVE | NA | Sree | 3- Completed
S3 | S3 | US-5 | Connecting Front end to Backend UI | MUST HAVE | NA | Sree | 3- Completed
S4 | S4 | US-6 | Modifications in UI | MUST HAVE | NA | Sree | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | T-1 | Introduction of Project | 2026-02-10 | 2026-02-11 | Sree | Others | 3- Completed
US-1 | T-2 | System setup- Install Python & Import libraries | 2026-02-12 | 2026-02-13 | Sree | Others | 3- Completed
US-1 | T-3 | Learning Parallel Processing & Multiprocessing | 2026-02-13 | 2026-02-14 | Sree | Others | 3- Completed
US-1 | T-4 | Text Handling & Database creation | 2026-02-13 | 2026-02-16 | Sree | Coding | 3- Completed
US-2 | T-5 | Database collection (News Articles) | 2026-02-17 | 17/2/26 | Sree | Others | 3- Completed
US-3 | T-6 | Dynamic chunking (by_lines & by words) | 18/2/26 | 19/2/26 | Sree | Coding | 3- Completed
US-3 | T-7 | Parallel processing implementation | 19/2/26 | 22/2/26 | Sree | Coding | 3- Completed
US-3 | T-8 | Connecting results to SQLlite | 22/2/26 | 25/2/26 | Sree | Coding | 3- Completed
US-3 | T-9 | Modifications in Backend codes | 25/2/26 | 2/3.26 | Sree | Coding | 3- Completed
US-3 | T-10 | Uploading Files to GitHub Repository | 2026-02-03 | 2026-03-03 | Sree | Others | 3- Completed
US-4 | T-11 | Building Basic User Interface | 2026-05-03 | 2026-10-03 | Sree | Design | 3- Completed
US-4 | T-12 | Adding extra Functionalities | 13/3/26 | 18/3/26 | Sree | Design | 3- Completed
US-5 | T-13 | Modifications in UI | 18/3/26 | 23/3/26 | Sree | Design | 3- Completed
US-6 | T-14 | Final Testing Phase | 23/3/26 |  | Sree | System Test | 2- In Progress

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
US-1 |  | Implementation of parallel processing | Discussed in session & clarified
US-3 |  | Dynamic chunking | Contacted with Mentor
US-4 |  | UI Integration check | Shared with mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7